## Executive Summary
SRE Agent — Confidence Calibration Report
2026-08-27
What this is
A test of the agent's confidence-scoring system against 14 real, controlled Kubernetes failure scenarios -- built to check whether the confidence number the agent reports actually reflects how good the answer is.
Headline result
Two real bugs were found and fixed during this exercise -- both more important than the original goal of tuning confidence weights.
1. Wrong-target investigation bug (critical)
One test case ('notification-svc shows no endpoints') caused the agent to investigate a completely different, unrelated pod -- and score that wrong answer 95% confidence. Root cause: the agent's internal planning steps never saw the original incident description, only a short summary that can go blank for incidents about a Service rather than a Pod. Fixed and live-verified same day.
2. Sidecar/Istio container bug (high)
Confirmed a real-world issue: on any pod running a sidecar container (Istio, Envoy, etc.), the agent had no way to specifically request the application container's logs, and Kubernetes itself silently returns the sidecar's logs instead. Reproduced live, fixed, and verified against a real 2-container test pod.
Confidence scoring itself
Working as intended on 13 of 14 cases (full detail on the Raw Results tab). A separate finding, already fixed same day: one scoring component (resource_identity_match) could score a correct answer as 0.0 purely because of how a supporting AI step phrased a description -- fixed to use the real tool-call data instead of AI-written text, live-verified.
Weight re-tuning (the original ask)
Paused. The routing bug above meant the original baseline data included at least one investigation of the wrong thing entirely -- tuning weights against that would have been tuning against bad data. Recommend re-running this same 14-case baseline now that both fixes are live, before any weight changes.
How real is this test
All 14 scenarios ran against real, live-broken Kubernetes pods on the test cluster -- not simulated. The confidence-scoring code itself is identical to what runs in the deployed agent; verified directly in the source, and spot-checked against the real deployed agent for one case.

## Raw Results
Case | Scenario | Confidence | Band | Outcome | Root Cause Found | Time (s) | Notes
crashloop-001 | Pod keeps crashing (CrashLoopBackOff) | 0.95 | high_confidence | confirmed | The application within the 'crasher' container in pod crashloop-pod exited with code 1, simulating a crash (ev_001, ev_003). | 39.6
oomkilled-001 | Pod repeatedly OOMKilled | 0.65 | review_required | probable | The 'memory-hog' container within 'oomkilled-pod' is intentionally exceeding its memory limits, leading to repeated OOMKills (ev_004). | 173.3
imagepull-001 | Pod cannot pull its container image | 0.95 | high_confidence | confirmed | The pod 'imagepull-pod' is failing to start because it is configured to pull a nonexistent image 'gcr.io/google-containers/nonexistent-image:v99.9.9' (ev_003). | 66.8 | Original run hit a one-off model-response parsing failure (system correctly reported 'insufficient evidence' instead of guessing -- a real, working safety behavior). Re-ran cleanly: 0.95, correct root cause. Clean value shown.
configmap-001 | Pod stuck ContainerCreating -- ConfigMap missing | 0.9 | high_confidence | confirmed | The pod 'auth-service' is stuck in 'ContainerCreating' status because the ConfigMap 'app-config' required for volume 'config-volume' is missing (ev_001, ev_002, ev_003). | 64.8
init-001 | Pod stuck Init -- init container blocked | 0.9625 | high_confidence | confirmed | The 'wait-for-db' init container in pod 'inventory-service' is blocking startup because 'db-service' is unavailable (ev_003). | 61.8
selector-001 | Service has zero endpoints (selector mismatch) | 0.95 | high_confidence | confirmed | The 'auth-service' pods are failing to mount a required volume because the 'app-config' ConfigMap is not found (ev_001, ev_002). This prevents the pods from starting (ev_003). | 63.4 | THIS is the case that exposed the critical routing bug (issue #209): originally investigated a completely unrelated pod at 0.95 confidence -- wrong answer, high confidence. Root cause found, fixed, and live-verified same day (now correctly targets notification-svc). Value shown is PRE-FIX -- kept for the record, not corrected, since it's the actual finding that mattered most from this exercise.
cascading-001 | One pod crashes because a dependency (DB) is OOMKilled | 0.65 | review_required | probable | The order-api pod 'order-api-65fdffc6cb-cmmrz' is in CrashLoopBackOff because its 'order-api' container fails to start due to a 'Connection refused' error when trying to connect to 'order-db' (ev_003, ev_004). | 106.1
pending-001 | Pod stuck Pending, never scheduled | 0.925 | high_confidence | confirmed | The pod batch-worker-7 does not exist in the sre-test-cluster, as indicated by multiple 'NotFound' errors (ev_002, ev_004). | 88.3
onprem-001 | Pod on a different (on-prem) cluster | 0 | insufficient_evidence | insufficient_evidence | No evidence was extracted, so root cause cannot be determined. | 8.4
insufficient-evidence-001 | Reported pod no longer exists | 0.825 | review_required | probable | Pod ghost-pod-42 was deleted, and its associated deployment 'ghost' is also not found, indicating a deletion of the deployment (ev_002, ev_004). | 83.7
conflicting-evidence-001 | Evidence sources disagree on cause | 0 | insufficient_evidence | insufficient_evidence | The model's response could not be parsed, so no root cause was produced. | 120
ambiguous-routing-001 | Vague report, no pod/service named | 0 | insufficient_evidence | insufficient_evidence | No evidence was extracted, so root cause cannot be determined. | 4.8
mcp-gateway-failure-001 | Data-source connectivity failure scenario | 0.925 | high_confidence | confirmed | The pod 'edge-gateway-1' does not exist or was deleted from the 'sre-test-cluster' (ev_001, ev_003). | 45.6
secret-001 | Pod stuck ContainerCreating -- Secret missing | 0.7 | review_required | probable | The user-service pod failed to start because the 'db-credentials' secret was not found (ev_001, ev_002). This was compounded by initial scheduling failures due to insufficient CPU and untolerated taints (ev_001). | 89.4