## Project Tracker
ID | Phase | Workstream | Task | Status | Priority | Owner | Target Date | Notes
1 | Phase 0 | Protect Current Working Setup | Capture and document the known-good deployment | Completed | High |  |  | Known-good deployment documented.
2 | Phase 0 | Protect Current Working Setup | Tag/version known-good deployment state | In Progress | Medium |  |  | Keep an explicit rollback reference/tag.
3 | Phase 0 | Protect Current Working Setup | Back up/reference Agent Engine, Agent Identity, Agent Gateway and MCP configurations | Completed | High |  |  | Configuration and architecture references exist.
4 | Phase 0 | Protect Current Working Setup | Capture successful end-to-end investigation with logs and traces | In Progress | High |  |  | Corrected 2026-08-13: was marked Completed, but reliable full-path trace evidence does not currently exist. A real deployed investigation (run_20260813_045745_ainm) produced no exported Cloud Trace span at all; this project's entire Cloud Trace history has only 2 old traces (2026-08-09), one span each. Structured logs + GCS evidence capture ARE working (verified repeatedly this session), but "logs and traces" together, as this task states, is not yet true. Tracked by GitHub #130 / tracker ID 62.
5 | Phase 0 | Protect Current Working Setup | Document rollback and recovery steps | In Progress | High |  |  | Needs final validation.
6 | Phase 0 | Protect Current Working Setup | Perform rollback test | Not Started | High |  |  | Required before production approval.
7 | Phase 0 | Protect Current Working Setup | Perform disaster-recovery drill | Not Started | Medium |  |  | Production readiness validation.
8 | Phase 1 | Production Readiness | Consolidate production roadmap | In Progress | High |  |  | Use this tracker as the consolidated source of truth.
9 | Phase 1 | Production Readiness | Complete Production Readiness Review | In Progress | Critical |  |  | Multiple launch gaps remain.
10 | Phase 1 | Production Readiness | Map architecture, data flow and trust boundaries | In Progress | High |  |  | Architecture exists; trust-boundary validation remains.
11 | Phase 1 | Production Readiness | Validate Agent Gateway architecture | In Progress | High |  |  | Gateway works; final production validation remains.
12 | Phase 1 | Production Readiness | Validate Agent Identity architecture | Completed | High |  |  | Implemented.
13 | Phase 1 | Production Readiness | Validate IAM and identities | In Progress | Critical |  |  | Cross-project and least-privilege review remains.
14 | Phase 1 | Production Readiness | Confirm Kubernetes access is read-only | Completed | Critical |  |  | Read-only controls implemented.
15 | Phase 1 | Production Readiness | Review secrets and sensitive-data handling | In Progress | High |  |  | Final security review required.
16 | Phase 1 | Production Readiness | Validate evidence storage | In Progress | High |  |  | Auditable persistence needs final validation.
17 | Phase 1 | Production Readiness | Final production-readiness approval | Not Started | Critical |  |  | Gated on launch blockers.
18 | Phase 2 | Agent Gateway & Model Armor | Document Agent Gateway certificate issue and confirmed fix | Completed | Medium |  |  | Earlier issue no longer blocks Terraform-managed path.
19 | Phase 2 | Agent Gateway & Model Armor | Confirm current Agent Gateway configuration | Completed | High |  |  | Gateway deployed and working.
20 | Phase 2 | Agent Gateway & Model Armor | Final Agent Gateway production validation | In Progress | High |  |  | Validate complete traffic/security behavior.
21 | Phase 2 | Agent Gateway & Model Armor | Confirm current Model Armor configuration | In Progress | High |  |  | Templates exist; live content inspection not active.
22 | Phase 2 | Agent Gateway & Model Armor | Retest Model Armor in clean environment | In Progress | High |  |  | Controlled validation pending.
23 | Phase 2 | Agent Gateway & Model Armor | Test Model Armor with Agent Identity, IAP and Agent Gateway | Not Started | High |  |  | Use supported regional integration.
24 | Phase 2 | Agent Gateway & Model Armor | Define separate Model Armor policies for input/evidence/output | Not Started | Medium |  |  | Pending architecture validation.
25 | Phase 2 | Agent Gateway & Model Armor | Test Kubernetes logs/events for false positives | Not Started | Medium |  |  | Needed before enforcement.
26 | Phase 2 | Agent Gateway & Model Armor | Confirm Model Armor failure/fallback behaviour | Not Started | High |  |  | Needs explicit failure-mode test.
27 | Phase 3 | RCA Output & Evidence | Evidence-backed RCA | Completed | Critical |  |  | Implemented.
28 | Phase 3 | RCA Output & Evidence | Evidence IDs on important RCA claims | Completed | Critical |  |  | Implemented.
29 | Phase 3 | RCA Output & Evidence | Prevent unsupported conclusions from being confirmed | Completed | Critical |  |  | Insufficient-evidence path exists.
30 | Phase 3 | RCA Output & Evidence | Executive-first RCA output redesign | In Progress | Medium |  |  | Hardening/simplification remains.
31 | Phase 3 | RCA Output & Evidence | Remove duplicated/weak root-cause claims | In Progress | High |  |  | Grounding-quality fixes remain.
32 | Phase 3 | RCA Output & Evidence | Supporting, contradicting and missing evidence | In Progress | High |  |  | Needs stronger deterministic handling.
33 | Phase 3 | RCA Output & Evidence | Affected-resource and incident-time information | In Progress | Medium |  |  | Time/resource validation needs improvement.
34 | Phase 3 | RCA Output & Evidence | Alternatives considered | In Progress | Medium |  |  | Dynamic alternative-cause handling incomplete.
35 | Phase 3 | RCA Output & Evidence | Service/user-impact detection | Blocked | Critical |  |  | Impact is not reliably derived yet.
36 | Phase 3 | RCA Output & Evidence | Human-approved remediation only | Completed | Critical |  |  | Core design rule.
37 | Phase 4 | Dynamic Investigation & Confidence | Separate Investigation Completeness and Root Cause Confidence | Completed | Critical |  |  | Two-score model implemented.
38 | Phase 4 | Dynamic Investigation & Confidence | Deterministic application-side confidence scoring | Completed | Critical |  |  | Implemented and tested.
39 | Phase 4 | Dynamic Investigation & Confidence | Contradiction handling | In Progress | High |  |  | Needs production hardening.
40 | Phase 4 | Dynamic Investigation & Confidence | Missing/failed/stale evidence penalties and caps | In Progress | High |  |  | Coverage bug remains in some failed-tool cases.
41 | Phase 4 | Dynamic Investigation & Confidence | Confidence calibration testing | Not Started | Medium |  |  | Compare confidence with actual RCA accuracy.
42 | Phase 4 | Dynamic Investigation & Confidence | Dynamic investigation loop | In Progress | Critical |  |  | Loop exists; correctness gaps remain.
43 | Phase 4 | Dynamic Investigation & Confidence | Dynamic hypothesis generation/testing | In Progress | High |  |  | Expected-vs-contradicting evidence loop incomplete.
44 | Phase 4 | Dynamic Investigation & Confidence | Allow insufficient evidence / unknown cause | Completed | Critical |  |  | Implemented.
45 | Phase 4 | Dynamic Investigation & Confidence | Support multiple possible causes | In Progress | Medium |  |  | Needs validation.
46 | Phase 5 | Testing & Evaluation | Automated Python test suite | Completed | High |  |  | Substantial coverage exists.
47 | Phase 5 | Testing & Evaluation | Terraform native tests | Completed | High |  |  | Implemented.
48 | Phase 5 | Testing & Evaluation | Golden evaluation dataset | Completed | High |  |  | Foundation dataset exists.
49 | Phase 5 | Testing & Evaluation | Evaluation runner | Completed | High |  |  | Implemented.
50 | Phase 5 | Testing & Evaluation | Unit tests for all LangGraph nodes | In Progress | High |  |  | Several direct node tests remain.
51 | Phase 5 | Testing & Evaluation | Full compiled graph E2E test | Blocked | Critical |  |  | Required production validation gap.
52 | Phase 5 | Testing & Evaluation | Entrypoint → Agent → MCP → Evidence → Scorer E2E evaluation | Blocked | Critical |  |  | Must prove full workflow.
53 | Phase 5 | Testing & Evaluation | Expand production-like golden scenarios | In Progress | High |  |  | Add complex/conflicting/stale/missing evidence.
54 | Phase 5 | Testing & Evaluation | MCP failure and wrong-cluster safety tests | In Progress | Critical |  |  | Routing-safety testing incomplete.
55 | Phase 5 | Testing & Evaluation | LLM-judge evaluation | Not Started | Low |  |  | Secondary evaluation only.
56 | Phase 5 | Testing & Evaluation | Regression tests for fixed issues | In Progress | High |  |  | Continue adding for every fix.
57 | Phase 5 | Testing & Evaluation | Structured engineer-feedback process | Deferred | Low |  |  | Phase 2 enhancement.
58 | Phase 6 | Observability & Reliability | Structured logging | Completed | High |  |  | Implemented.
59 | Phase 6 | Observability & Reliability | Distributed tracing foundation | Completed | High |  |  | Implemented.
60 | Phase 6 | Observability & Reliability | Investigation/run IDs | Completed | High |  |  | Implemented.
61 | Phase 6 | Observability & Reliability | Metrics and alert policies | Completed | High |  |  | 11 metrics and 11 alerts exist.
62 | Phase 6 | Observability & Reliability | Cloud Trace export restored and verified end-to-end | Completed | High |  |  | Cloud Trace export restored and verified end-to-end -- 2026-08-13. Three root causes fixed (PR #136, #137): lazy tracer init losing setup race, wrong Cloud Trace hostname, wrong gRPC protocol binding for Cloud Trace. Live proof: run_20260813_222248_ybag -- flush_traces result=True, real trace ada23f5a144e8b327fe6fc51c3a426b4 with 54 correlated spans (outer + all LangGraph nodes + Gemini calls), metadata-only content confirmed. GitHub #130 and #29 closed. NOTE: this covers Cloud Trace ONLY -- the separate Cloud Logging observability-write 403 is NOT fixed by this work, tracked separately as tracker ID 152 / GitHub #139.
63 | Phase 6 | Observability & Reliability | Operational dashboard | Not Started | Medium |  |  | Needed for operations.
64 | Phase 6 | Observability & Reliability | Controlled delivery test for every alert | Not Started | High |  |  | Configured alerts must be proven.
65 | Phase 6 | Observability & Reliability | Mitigate managed Reasoning Engine stream timeout / high investigation latency | Completed | Critical |  |  | RESOLVED 2026-08-15 via native stream_query() (PR #160, merge commit 0a15f93). Deployment: Agent Engine updated in place (Terraform 0 add/1 change/0 destroy, Agent Engine ID 7801582006105538560 unchanged, createTime unchanged, Agent Identity and Agent Gateway attachment preserved). Live E2E run_id run_20260815_121835_mmmq: 315.3s duration (past the original ~300s transport boundary), 34 stream progress events, 5 real GKE Remote MCP tool calls/evidence collected, truthful final RCA returned, no stream-timeout error. Native streaming (--stream-query) is now the supported long-running invocation path. Synchronous query() remains available but keeps its known ~300s managed transport limit. asyncQuery/run_query_job (#156) stays in repo, experimental/Google-blocked, not required for this resolution. Follow-up (separate, does not reopen this): Cloud Trace span-fragmentation regression found during validation, tracked as new issue #161 -- not yet added as its own tracker row, pending approval.
66 | Phase 6 | Observability & Reliability | Define retry, timeout and backoff behaviour | In Progress | Critical |  |  | Align client/backend/tool behavior.
67 | Phase 6 | Observability & Reliability | Define investigation/tool/token/cost limits | In Progress | High |  |  | Monitoring/token-budget slice DONE 2026-08-12 (PR #102, commit 85030c8). Deployed, live-validated: real MAX_TOKENS_PER_RUN=100000 confirmed on the live engine, real investigation tokens_total correctly metered (1 data point per run, not duplicated across per-node events), synthetic threshold test opened a real alert incident (0.obcxlxk5jaf5). Remaining: removing the inaccurate hardcoded local dollar-cost estimation -- separate, not started. GitHub issue #63 itself is closed (was about a DIFFERENT bug, the Flash/Pro pricing mismatch, already fixed) -- this remaining work has no dedicated GitHub issue of its own yet.
68 | Phase 6 | Observability & Reliability | Create operational runbooks | In Progress | Medium |  |  | Needs final procedures.
69 | Phase 7 | Multi-Cluster Scalability | Multi-cluster registry | Completed | Critical |  |  | Terraform-managed registry implemented.
70 | Phase 7 | Multi-Cluster Scalability | Prevent Terraform from removing registered clusters accidentally | Completed | Critical |  |  | Registry ownership bug fixed.
71 | Phase 7 | Multi-Cluster Scalability | Deterministic cluster-type routing | Completed | Critical |  |  | Implemented.
72 | Phase 7 | Multi-Cluster Scalability | Cluster onboarding/update/removal/rollback workflow | In Progress | High |  |  | Needs repeatable validation.
73 | Phase 7 | Multi-Cluster Scalability | Unknown/missing-cluster safe-stop validation | Completed | Critical |  |  | PR #108 merged (d5fe1b2a), deployed (run 31585553325, engine 7801582006105538560 updated in-place, confirmed not recreated). Live E2E test run_20260812_101219_mbwh: all 7 required checks passed with log-level evidence -- loop_exit_reason=cluster_unresolved, cluster_routing_method=unresolved, zero MCP/tool calls (node sequence proves it), zero memory recall/save, truthful response, no unsupported root cause. Issue #73 closed.
74 | Phase 7 | Multi-Cluster Scalability | Cross-project IAM for additional clusters | In Progress | Critical |  |  | Required for production scale.
75 | Phase 7 | Multi-Cluster Scalability | Namespace and cluster access controls | In Progress | High |  |  | Needs final isolation model.
76 | Phase 7 | Multi-Cluster Scalability | Concurrency/quota/failure-isolation testing | Not Started | High |  |  | Scale testing remains.
77 | Phase 7 | Multi-Cluster Scalability | Repeatable multi-cluster onboarding documentation | In Progress | Medium |  |  | Runbook remains.
78 | Phase 8 | MCP Tool Architecture | GKE Remote MCP primary source | Completed | Critical |  |  | Working.
79 | Phase 8 | MCP Tool Architecture | MCP registry and deterministic routing | Completed | Critical |  |  | Implemented.
80 | Phase 8 | MCP Tool Architecture | Custom read-only Kubernetes MCP code | Completed | High |  |  | Code exists with mutation guards.
81 | Phase 8 | MCP Tool Architecture | Source-agnostic MCP interface | In Progress | High |  |  | Needs stronger common abstraction.
82 | Phase 8 | MCP Tool Architecture | Normalize evidence returned by MCP servers | In Progress | High |  |  | Common contract not fully generalized.
83 | Phase 8 | MCP Tool Architecture | Repeatable MCP-server onboarding process | In Progress | Medium |  |  | Needs documented contract.
84 | Phase 8 | MCP Tool Architecture | Output trimming and evidence validation | In Progress | High |  |  | Important for cost and grounding.
85 | Phase 8 | MCP Tool Architecture | Timeout/retry/rate-limit/audit requirements | In Progress | High |  |  | Needs production contract.
86 | Phase 8 | MCP Tool Architecture | Deploy Custom Kubernetes MCP in cloud | Blocked | Critical |  |  | Required for non-GKE path.
87 | Phase 8 | MCP Tool Architecture | Prevent arbitrary shell/write operations | Completed | Critical |  |  | Read-only controls exist.
88 | Phase 9 | Cost & Performance | Detailed token telemetry | Completed | High |  |  | Per-call and per-run telemetry exists.
89 | Phase 9 | Cost & Performance | Measure investigation cost and latency | In Progress | High |  |  | Latency regression currently significant.
90 | Phase 9 | Cost & Performance | Reduce unnecessary investigation loops | In Progress | High |  |  | Part of dynamic investigation hardening.
91 | Phase 9 | Cost & Performance | Trim and deduplicate evidence before model calls | In Progress | High |  |  | Further optimization needed.
92 | Phase 9 | Cost & Performance | Per-investigation token/cost budgets | In Progress | High |  |  | Guardrails not finalized.
93 | Phase 9 | Cost & Performance | Review model selection per workflow stage | In Progress | Medium |  |  | Provider-neutral adapter exists.
94 | Phase 9 | Cost & Performance | Advanced caching and dynamic pricing | Deferred | Low |  |  | Phase 2 optimization.
95 | Phase 10 | PagerDuty Integration | Design PagerDuty-triggered workflow | Not Started | Critical |  |  | Required Phase 1 integration.
96 | Phase 10 | PagerDuty Integration | Authenticated Cloud Run webhook receiver | Not Started | Critical |  |  | No implementation yet.
97 | Phase 10 | PagerDuty Integration | Pub/Sub buffering and investigation workers | Not Started | High |  |  | Planned scalable path.
98 | Phase 10 | PagerDuty Integration | Webhook verification and replay protection | Not Started | Critical |  |  | Security requirement.
99 | Phase 10 | PagerDuty Integration | Incident deduplication and idempotency | Not Started | Critical |  |  | Production requirement.
100 | Phase 10 | PagerDuty Integration | Trigger read-only investigation from incident | Not Started | Critical |  |  | Core integration goal.
101 | Phase 10 | PagerDuty Integration | Post RCA draft back to PagerDuty | Not Started | High |  |  | Include evidence/confidence/unknowns/next checks.
102 | Phase 11 | Additional MCP Sources | Prometheus integration | Not Started | Low |  |  | Future phase.
103 | Phase 11 | Additional MCP Sources | Grafana integration | Not Started | Low |  |  | Future phase.
104 | Phase 11 | Additional MCP Sources | Elastic / Elasticsearch integration | Not Started | Low |  |  | Future phase.
105 | Phase 11 | Additional MCP Sources | Cloud Logging integration | Not Started | Medium |  |  | Future evidence source.
106 | Phase 11 | Additional MCP Sources | Confluence/runbook integration | Not Started | Low |  |  | Future phase.
107 | Phase 11 | Additional MCP Sources | GitHub integration | Not Started | Low |  |  | Future phase.
108 | Phase 11 | Additional MCP Sources | Normalized traceable evidence for every source | Not Started | High |  |  | Depends on MCP abstraction.
109 | Phase 12 | On-Premises Kubernetes | Validate Fleet / Connect Gateway concept | In Progress | High |  |  | Manual prototype/concept work exists.
110 | Phase 12 | On-Premises Kubernetes | Custom MCP → Connect Gateway production path | Not Started | Critical |  |  | Production path not proven.
111 | Phase 12 | On-Premises Kubernetes | Validate supported agent-authentication model | Not Started | High |  |  | Need short-lived supported auth.
112 | Phase 12 | On-Premises Kubernetes | Validate IAM and Kubernetes RBAC | Not Started | Critical |  |  | Production security requirement.
113 | Phase 12 | On-Premises Kubernetes | Test read-only access to real on-prem cluster | Not Started | High |  |  | Prototype is not production validation.
114 | Phase 12 | On-Premises Kubernetes | Review audit logs, latency, quotas and isolation | Not Started | High |  |  | Reliability requirement.
115 | Phase 12 | On-Premises Kubernetes | Document onboarding/removal runbook | Not Started | Medium |  |  | After path validation.
116 | Phase 13 | Security & Supply Chain | Agent Identity / no static service-account keys | Completed | Critical |  |  | Implemented.
117 | Phase 13 | Security & Supply Chain | Read-only Kubernetes tooling | Completed | Critical |  |  | Implemented.
118 | Phase 13 | Security & Supply Chain | Complete final IAM review | In Progress | Critical |  |  | Cross-project/least-privilege review remains.
119 | Phase 13 | Security & Supply Chain | Kubernetes RBAC scoping | In Progress | Critical |  |  | Needs production validation.
120 | Phase 13 | Security & Supply Chain | MCP authentication and authorization review | In Progress | High |  |  | Needed before adding sources.
121 | Phase 13 | Security & Supply Chain | Agent Gateway security validation | In Progress | High |  |  | Final production review.
122 | Phase 13 | Security & Supply Chain | Model Armor controlled validation | In Progress | High |  |  | Not active in live path.
123 | Phase 13 | Security & Supply Chain | Supply-chain and CI hardening | In Progress | Medium |  |  | Pinning/CI/container hardening remain.
124 | Phase 13 | Security & Supply Chain | VPC-SC / additional network hardening | Deferred | Low |  |  | Phase 2 unless required earlier.
125 | Phase 14 | ADK Migration Assessment | ADK architecture comparison | Deferred | Low |  |  | Do not disrupt working LangGraph path during Phase 1.
126 | Phase 14 | ADK Migration Assessment | ADK proof of concept and parity evaluation | Deferred | Low |  |  | Phase 2.
127 | Phase 14 | ADK Migration Assessment | Migration decision | Deferred | Low |  |  | After MVP is stable.
128 | Final | Final Production Approval | Final architecture review | Not Started | Critical |  |  | Production gate.
129 | Final | Final Production Approval | Final security review | Not Started | Critical |  |  | Production gate.
130 | Final | Final Production Approval | Final IAM review | Not Started | Critical |  |  | Production gate.
131 | Final | Final Production Approval | Final Model Armor report/decision | Not Started | High |  |  | Production gate.
132 | Final | Final Production Approval | Final RCA accuracy and confidence evaluation | Not Started | Critical |  |  | Production gate.
133 | Final | Final Production Approval | Monitoring and alert-delivery validation | Not Started | Critical |  |  | Production gate.
134 | Final | Final Production Approval | Rollback and recovery testing | Not Started | Critical |  |  | Production gate.
135 | Final | Final Production Approval | Document known limitations and accepted risks | Not Started | High |  |  | Production gate.
136 | Final | Final Production Approval | Human approval before production rollout | Not Started | Critical |  |  | Required by design.
137 | Phase 1 | Production Readiness | Issue #31: SSE parser can silently return an empty first frame as success -- workflow/output correctness risk | Completed | High |  |  | Fixed and deployed 2026-08-12 (PR #111, commit d4646d7). 6 new tests, full suite 153/153. Deploy confirmed update-in-place. Live regression evidence via CI smoke test (real MCP round-trip, mcp_latency_s=3.49, SMOKE TEST PASSED) plus a manual live run whose 3 MCP calls all succeeded before an unrelated timeout. Issue #31 closed.
138 | Phase 1 | Production Readiness | Issue #87: Terraform gateway self-heal can auto-recreate the production Reasoning Engine unattended -- infrastructure/deployment safety risk | Completed | High |  |  | Correction 2026-08-12: user caught that this was already fixed. The self-heal -replace= auto-recreate step this issue described was removed the day after filing (2026-08-10, PR #93) as a side effect of an unrelated migration -- gateway attach moved to native Terraform management. Confirmed via repo-wide grep: no -replace= or self-heal pattern exists anywhere. Issue #87 closed with evidence. Never actually required implementation work.
139 | Phase 1 | Production Readiness | Issue #64: google_billing_budget shown in architecture docs is not provisioned in Terraform | Completed | Low |  |  | Closed 2026-08-12, no code change needed -- docs/governance/cost-management.md (verified 2026-08-08) already correctly states cost tooling is PLANNED, never claimed an automated budget alert exists. Confirmed no google_billing_budget resource anywhere in iac/. Real automated budget alerting deferred as a separate future decision (financial/IAM scope), not bundled here.
140 | Phase 1 | Production Readiness | Issue #92: Agent has no pod-log-read permission on the target GKE cluster -- logs unavailable for every incident | Completed | P0-quick-fix |  |  | Corrected + live-validated 2026-08-12. Real root cause was NOT a missing IAM permission -- a K8s-native RoleBinding already existed on the cluster (applied 2026-07-28) but was bound to a stale reasoning-engine ID from before a redeploy. Fixed by updating the RoleBinding subject to the current engine ID, checked into k8s/rbac.yaml (PR #121), applied live. Verified: kubectl auth can-i get pods/log --as=<current engine> now returns yes (was no). Reverted the earlier Cloud IAM custom-role approach (PR #118) as unnecessary duplicate infra -- never actually deployed. Full end-to-end agent test blocked by a separate CPUS_ALL_REGIONS=12 quota (cost guardrail on personal account, not raised) -- kubectl auth can-i accepted as sufficient live evidence per user confirmation.
141 | Phase 1 | Production Readiness | Issue #67: resource_identity_match only checks cluster, ignoring namespace and pod | Completed | P1-small-fix |  |  | Fixed 2026-08-12 (PR #125). resource_identity_match now checks namespace/pod via evidence resource_id field, not just cluster. 2 new regression tests, full suite 190/190 pass, deployed live via CI apply.
142 | Phase 1 | Production Readiness | Issue #68: time_correlation and freshness scoring do not evaluate real evidence timestamps | Completed | P1-small-fix |  |  | Fixed 2026-08-12 (PR #125). evidence_extractor.py now stamps real collected_at per evidence item; freshness/time_correlation use it instead of investigation-start proxy / flat binary. 4 new regression tests.
143 | Phase 1 | Production Readiness | Issue #69: investigation loop can exit while required evidence domains are still missing | Completed | P1-small-fix |  |  | Fixed 2026-08-12 (PR #125). Loop no longer exits on enough_evidence=True when missing_required_domains is non-empty and budget remains -- forces one more iteration. Real E2E proof cited in issue. 4 new regression tests.
144 | Phase 1 | Production Readiness | Issue #70: agent does not act on its own generated next investigative step before concluding | Completed | P1-small-fix |  |  | Partially fixed 2026-08-12 (PR #125) -- broaden-and-retry on NotFound added for list_k8s_events. Second half (force suggested tool call) covered by #69 fix instead (same root symptom, stronger mechanism). Issue auto-closed as a side effect of commit message wording -- see corrective comment on the issue. 6 new regression tests.
145 | Phase 1 | Production Readiness | Issue #71: MCP fallback audit trail records the requested tool, not what actually executed | Completed | P1-small-fix |  |  | Fixed 2026-08-12 (PR #125). tool_history/latest_tool_result now record call_tool()'s actual executed tool/mcp_source, not the pre-call request. 3 new regression tests.
146 | Phase 1 | Production Readiness | Issue #72: MCP fallback does not trigger on network errors and has an invalid tool mapping | Completed | P1-small-fix |  |  | Fixed 2026-08-12 (PR #125). Fallback now fires on network exceptions and empty responses too (not just non-200 status); removed 2 semantically-invalid tool mappings (get_k8s_cluster_info/list_k8s_api_resources -> list_pods); pod_name only sent to fallback targets that accept it. 9 new regression tests.
147 | Phase 1 | Production Readiness | Issue #74: Gemini token/cost/latency counters are process-global, not scoped per investigation | Completed | P1-small-fix |  |  | Fixed 2026-08-12 (PR #127). GeminiAdapter is cached process-wide and reused across investigations -- added reset_session(), called at the start of every investigation in agent/main.py investigate(). 5 new regression tests, full suite 195/195 pass.
148 | Phase 1 | Production Readiness | Issue #75: Duplicate completion log events not scoped by logName can double-count metrics | Completed | P1-small-fix |  |  | Fixed 2026-08-12 (PR #127). 8 of 9 completion-related log-based metrics in monitoring.tf were double-counting (2 separate completion events share overlapping field names). Restricted to event_type="sre_agent_run", matching the #63 token_usage fix. 9 new terraform tests, terraform plan clean (8 metrics update in-place).
149 | Phase 1 | Production Readiness | Issue #76: Full prompt/response content capture enabled in tracing at 100% sample rate | Completed | P1-small-fix |  |  | Completed 2026-08-13 (PR #133). Corrected compliance review found 3 more real content-capture paths beyond the original flag: agent/main.py sre.query span attribute (raw query text), agent/otel.py trace_node() exception handling (record_exception/Status/sre.node.error all sent exception message text), and both spans defaulted to OTel start_as_current_span()'s record_exception=True (auto-captures exception message on re-raise, independent of explicit handling -- caught by this PR's own regression test failing on first run). All fixed: sre.query removed, only exception TYPE recorded (sre.node.error_type), record_exception=False/set_status_on_exception=False on both span-creation sites. 3 new Python tests (real in-process OTel TracerProvider + InMemorySpanExporter, unique secret marker proven absent from all span data) + 2 new terraform tests. Full suite 200/200, terraform test 25/25, terraform plan clean. Deployed, Agent Engine ID unchanged (7801582006105538560). Live-queried the real deployed resource directly (Vertex AI REST API, not just terraform state): OTEL_INSTRUMENTATION_GENAI_CAPTURE_MESSAGE_CONTENT=false, OTEL_TRACES_SAMPLER_ARG=1.0 confirmed. Does NOT claim working Cloud Trace was validated -- #130 (Cloud Trace export appears broken) is separate and stays open.
151 | Phase 1 | Production Readiness | Issue #91: Evidence-domain coverage credits failed tool calls as if they succeeded | Completed | P0-quick-fix |  |  | Fixed 2026-08-13 (PR #131, merged as part of a bundled branch -- see PR for note). _evidence_domains_present() now excludes ev.get("ok")==False entries, fixing both required_evidence_coverage and independent_corroboration. 2 new regression tests, full suite 197/197 pass. Deployed, Agent Engine ID unchanged (7801582006105538560).
152 | Phase 6 | Observability & Reliability | Fix persistent Cloud Logging observability-write 403 (rca_builder.py) | Completed | P2-medium-fix |  |  | RESOLVED 2026-08-23. Root cause: default gRPC transport never resolved a registry match through Agent Gateway (agentGatewayInfo empty on every real call, unlike every other working destination). Fix: cloud_logging.Client(_use_grpc=False), matched by re-registering us-central1-logging as protocolBinding=HTTP_JSON (Cloud Trace untouched). Live-verified 3/3 clean deployed investigations (run_20260823_163628_epvi, run_20260823_164050_ltcl, run_20260823_164258_wrjv) -- real entries now in sre-agent-investigations, which had zero entries in 180 days before. PRs #174 (controlled test), #175 (rolled to all 4 sites). Corrects a wrong repo assumption that google-cloud-logging is gRPC-only -- it isn't, confirmed against the installed 3.15.0 client.
153 | 6 | Observability & Reliability | Fix Cloud Trace span fragmentation in native stream_query() investigations | Completed | High |  |  | Fixed 2026-08-15 (PR #163, merge commit 7f02061). Root cause: investigate_stream()'s outer sre_agent.investigation OTel context was lost across the generator's own yield/resume boundary -- confirmed via a live diagnostic deployment (PR #162) showing context valid through points A/B, invalid immediately after the first yield (point C), same OS thread throughout. Fix: explicit OTel context capture/reattach around every graph.stream() iterator advancement in agent/main.py. Verified live: run_20260815_230251_iwqp produced one correlated trace with all 54 spans (sre_agent.investigation -> langgraph.* -> gen_ai.chat), matching the #130-validated synchronous baseline span count. GitHub #161 closed.
154 | 6 | Observability & Reliability | Resolve Agent Platform Console Traces/Telemetry view not updating after OTel provider fix (#164) | In Progress | High |  |  | FIXED (app side): our own OTel tracer-provider race. #130's fix (PR #136) made our tracer initialize early in set_up() and reliably win OpenTelemetry's one-time global-provider race (confirmed live: 11/11 workers), blocking Agent Engine's managed provider from installing. PR #165 (merge commit ee65b69, deployed 2026-08-16) stopped competing for that slot -- get_tracer() now builds its own local TracerProvider -- restoring the managed tracer path. Verified live: Google-owned Model Armor spans reappeared in Cloud Trace (never seen before this fix). WORKING: Cloud Trace collection itself. Live run run_20260816_083409_lpak produced 54 correctly-parented spans. STILL UNRESOLVED: the Agent Platform Console's Traces tab has not updated since 2026-08-13, and the Deployments list's Telemetry collection column still reads 'Learn more', not 'Enabled'. ROOT CAUSE UNCONFIRMED (Console side). Three config-level hypotheses tested live and ruled out 2026-08-14..16, each reverted after: sync vs stream invocation method; OTEL_INSTRUMENTATION_GENAI_CAPTURE_MESSAGE_CONTENT (boolean and correct-enum values); OTEL_SEMCONV_STABILITY_OPT_IN (never previously set). That was the last realistic officially-documented config lead. Google support case drafted, NOT yet submitted. GitHub #164 remains OPEN. Use Cloud Trace directly instead of the Console tab until it closes.
155 | 1 | Production Readiness | Issue #77: CI runs no tests, linting, or security scanning on pull requests | Completed | P2-medium-fix |  |  | Fixed and deployed (PR #141): python-tests.yml added -- pytest, blocking ruff, pip-audit, a separate mcp-pytest job. Live-validated 2026-08-20: deploy run https://github.com/AshminPy/sre-agent-gateway/actions/runs/32427392189 -- a real investigation (imagepull scenario) completed in ~90s with a correct root cause and no #103-style timeout, the required clean canary. GitHub #77 closed.
156 | 1 | Production Readiness | Issue #78: CI path filters skip tests/, scripts/, eval/, and iac/gke-access/ | Completed | P2-medium-fix |  |  | Fixed and deployed (PR #141), scoped correctly per its own 2026-08-14 Correction: eval/** and iac/gke-access/** intentionally excluded (iac/gke-access is a separate Terraform stack; both terraform workflows run working-directory: iac/agent, so adding that path would validate the wrong stack -- deferred to a later, unfiled audit item, not this issue). Live-validated by the same canary as #77: https://github.com/AshminPy/sre-agent-gateway/actions/runs/32427392189. GitHub #78 closed.
157 | 1 | Production Readiness | Issue #94: Recurring terraform plan drift: TELEMETRY env var re-add + source_archive mismatch on sre_agent | Completed | P2-medium-fix |  |  | Fixed (PR #157, merged 2026-08-20): removed the GOOGLE_CLOUD_AGENT_ENGINE_ENABLE_TELEMETRY declaration from agent_engine.tf -- Google's own provider code unconditionally skips this var when reading state back, so declaring it made every plan re-propose adding it forever. Deployed and applied cleanly: run https://github.com/AshminPy/sre-agent-gateway/actions/runs/32427392189, Apply step succeeded, 0 errors. Second cause (historical source_archive drift from the pre-#93 out-of-band script) was already expected to self-resolve; worth one more terraform plan check in a future session, not a new issue. GitHub #94 closed.
158 | 3 | RCA Output & Evidence | Container-aware evidence collection and attribution (multi-container/sidecar pods) | Not Started | Critical |  |  | Confirmed 2026-08-21/22: ALL workloads on the target GKE Autopilot clusters run an Istio sidecar -- this affects every investigation, not an edge case. Confirmed gap, 3 layers, read directly from code: (1) agent/mcp_client.py:306-317's GKE Remote MCP payload builder for get_k8s_logs never forwards a container argument even though the API supports one (custom MCP's mcp/tools/logs.py already does this correctly); (2) agent/nodes/evidence_extractor.py's evidence schema has no container field and never surfaces describe_pod_detail's own containers/container_statuses into the evidence the LLM reasons over; (3) agent/prompts.py's tool-selection prompt has no language teaching the model that a pod can have multiple containers, and mcp_router.py's auto-fill only ever sets namespace/pod. Scope, deliberately narrow -- data plumbing and prompt fix, not a redesign: forward the container arg on the GKE path, surface containers/container_statuses into key_facts, add container-selection guidance to the tool-selection prompt, add a container field to the evidence schema. Required before Milestone 1 (GKE pilot) per management direction 2026-08-22 -- every pilot target has this. See EXT-003 (External Dependencies worksheet) for the corresponding real work-cluster observation.
159 | 6 | Observability & Reliability | Issue #139 fix rolled out to tool_executor.py/mcp_router.py/gcs_client.py | In Progress | P2-medium-fix |  |  | Same _use_grpc=False fix as row 152's rca_builder.py resolution, applied to the 3 sibling call sites sharing the identical pattern (sre-agent-tool-failures, sre-agent-routing-failures, sre-agent-evidence-storage-failures). PR #175 merged and deployed (CI run 32653113035, smoke test passed). NOT yet live-validated -- these 3 only write on a genuine tool/routing/evidence-storage failure, which did not occur naturally in the 3 confirmation runs used to validate row 152. Completion requires: a real failure of each kind occurring live with the corresponding log entry confirmed written, no 403. Also open: the new HTTP_JSON-transported entries show resource.type=cloud_run_revision, not aiplatform.googleapis.com/ReasoningEngine -- the 5 alerts tied to these loggers (gke_mcp_failures, custom_mcp_failures, repeated_tool_failures, routing_failures, evidence_storage_failures) need their own resource.type re-check before assuming PR #173's fix pattern applies.

## Dashboard
SRE Agent Project Dashboard
Metric | Value |  | Priority | Count
Total Tasks |  |  | Critical
Completed |  |  | High
In Progress |  |  | Medium
Blocked |  |  | Low
Not Started |  |  | Deferred
Waiting on Google Support
Current Priority Focus
Order | Focus | Status | Why It Matters
1 | Fix client timeout / investigation latency | Blocked | Live runs can exceed the client timeout.
2 | Restore reliable pod-log access | Blocked | Missing logs directly reduces investigation quality.
3 | Close confidence/evidence correctness gaps | In Progress | Confidence must reflect successful, fresh evidence.
4 | Finish routing safety and multi-cluster IAM | In Progress | Wrong-cluster/default routing is a production safety risk.
5 | Complete full E2E evaluation | Blocked | Need proof the entire workflow works together.
6 | Deploy Custom MCP + validate Connect Gateway | In Progress | Required for production non-GKE/on-prem support.
7 | Build PagerDuty integration | Not Started | Required automated production trigger path.

## Phase Summary
Phase | Workstream | Total | Completed | In Progress | Blocked | Not Started | Waiting on Google Support
Phase 0 | Protect Current Working Setup
Phase 1 | Production Readiness
Phase 2 | Agent Gateway & Model Armor
Phase 3 | RCA Output & Evidence
Phase 4 | Dynamic Investigation & Confidence
Phase 5 | Testing & Evaluation
Phase 6 | Observability & Reliability
Phase 7 | Multi-Cluster Scalability
Phase 8 | MCP Tool Architecture
Phase 9 | Cost & Performance
Phase 10 | PagerDuty Integration
Phase 11 | Additional MCP Sources
Phase 12 | On-Premises Kubernetes
Phase 13 | Security & Supply Chain
Phase 14 | ADK Migration Assessment
Final | Final Production Approval

## Reference
Field | Value
Project | GCP AI SRE Agent
Repository | https://github.com/AshminPy/sre-agent-gateway
Reviewed | 2026-08-11
Statuses | Completed ¦ In Progress ¦ Not Started ¦ Blocked ¦ Deferred ¦ Waiting on Google Support
Priorities | Critical ¦ High ¦ Medium ¦ Low
Purpose | Master project tracker for roadmap and production readiness.
How to use | Update Status, Owner and Target Date in Project Tracker; summaries update automatically.

## External Dependencies
External ID | Area | Environment | Description | Impact | Owner | Status | Production Blocker | Required Action | Validation Required | Evidence / Notes
EXT-001 | K8s RBAC | Work cluster: multitenant-us-east4-non-production, ns sre-agent-poc | Agent needs read-only pod-log permission in the work namespace | get_k8s_logs cannot retrieve application logs on this cluster |  | Open | Yes - Critical | Grant least-privilege RBAC per the manual steps already provided (Role+RoleBinding, get/list/watch on pods, pods/log, events) | A real get_k8s_logs call returns requested pod/container logs, not an auth error | Environment onboarding item, not a sre-agent-gateway code bug. Manual remediation steps already provided separately. Not modified from this repo.
EXT-002 | Cluster onboarding | Work environment generally | Need a repeatable minimum-permission model so an engineer doesn't rediscover IAM/RBAC requirements per cluster | Slower, error-prone onboarding of each new work cluster |  | Open | No - process gap, not a hard blocker for Milestone 1 | Document the minimum RBAC/IAM template (based on k8s/rbac.yaml's real, applied pattern) as a reusable checklist | A second engineer onboards a cluster using only the documented steps, no rediscovery | Ties to tracker row 72/77 (Cluster onboarding workflow, repeatable onboarding documentation)
EXT-003 | Multi-container evidence | Work cluster (observed during real testing) | Multi-container pods (app + Istio sidecar) affected evidence selection during real testing. Confirmed 2026-08-22: ALL workloads on target GKE Autopilot clusters run an Istio sidecar. | Risk of incorrect RCA attribution when the wrong container's evidence is used |  | Open | Yes - Critical (every workload is affected, not an edge case) | Internal fix tracked as tracker row 158 (Container-aware evidence collection and attribution); this row records the environment observation that made it a confirmed Milestone-1 requirement | A controlled multi-container incident proves the agent selects/attributes evidence to the correct container and produces no false RCA | Confirms tracker row 158's code gap is real in practice, not just in theory